## Test Summary
Sprint Release Info
Sprint Release Version : 14 Sprint Release Planned Date : Sprint Release Actual Date :
QA Summary
User Stories Planned For Release | 34 | Pass : 25 Fail : 6 In-Progress: 3 ( 2 Epics@one clarification) Blocked: 0
Defects planned for Release( Not planned for current release) | 19 | Pass : 18 Fail : 1 (309 failed) In-Progress: Blocked: 0
Hot Fixes Planned for Release | 3 | Pass : 2 Fail : 0 In-Progress: 1 (501) Blocked: 0
Total | 56
Environments Info
Environments tested as part of Sprint release : Dev Environment Dev 2 Environment Staging Environment
Defects Info
Number of Regression Defects
Number of Sprint Defects (Sprint User stories)

## 2017_06_19_05_19_22_merqbiz
number | summary | QA Status
User Management Phase 2 User stories
29 | Epic [UM-2] Implement Company ACL | Its an Epic
498 | [regression-UM2] Fatal present when access order detail page | Verified and Pass
430 | [UM-2] [Area] Theme Buyer Company User List and Invitation Flow (Desktop and Tablet) | Verified and Pass
420 | [UM-2] [AREA] - Updated Seller First Time Sign in - Frontend Theming (Desktop and Tablet) | Verified and Pass
419 | [UM2] [AREA] - Updated Buyer First Time Sign in - Frontend Theming (Desktop and Tablet) | Verified and Pass
114 | [UM-2] Invite additional Buyers from Approved Buyer Company - email invitation. | Verified and Pass
115 | [UM-2] Invite additional Sellers from Approved Seller company - email invitation | Verified and Pass
416 | [UM-2] Seller Company User: Act only as Authorized | Dependent on 412 and 413
415 | [UM-2] Seller Company Admin: Change User Role | Verified and Pass
414 | [UM-2] Seller Company Admin: Manage User Roles | In Progress Assigned to Geoff for review
413 | [UM-2] Seller: Assign Pre-configured Role to Company User | Failed Able to accept/decline offers from homepage
412 | [UM-2] Seller: Assign Custom Role to Company User | Failed Observations noted | Accept/reject claims is not applicable remove those options from list
411 | [UM-2] Buyer Company Admin: Change User Role | Verified and Pass
410 | [UM-2] Buyer Company Admin: Manage User Roles | Verified and Pass
409 | [UM-2] Buyer Company User: Act only as Authorized | Verified and Pass
408 | [UM-2] Buyer: Assign Pre-configured Role to Company User | Verified and Pass
407 | [UM-2] Buyer: Assign Custom Role to Company User | Verified and Pass
397 | [UM-2] Seller: New Company User First Time Sign In Flow | Verified and Pass
396 | [UM-2] Admin: Seller Company User Invitation Email | Verified and Pass
395 | [UM-2] Seller Admin: Add User to Company with Invitation | Verified and Pass
394 | Epic [UM-2] Seller: Manage Company Membership Invitation Flow | Verified and Pass
497 | [Regression - UM2] Buyer: grid broken for non-admin users | Failed
390 | Epic [UM-2] Buyer: Manage Company Membership Invitation Flow | Verified and Pass
391 | [UM-2] Buyer Admin: Add User to Company with Invitation | Verified and Pass
392 | [UM-2] Admin: Buyer Company User Invitation Email | Failed | unable to login with buyer crdentials
393 | [UM-2] Buyer: New Company User First Time Sign In Flow | Verified and Pass
389 | [UM-2] Admin: Manage Seller Company User Role Assignment | Verified and Pass
388 | [UM-2] Admin: Manage Buyer Company User Role Assignment | Verified and Pass
387 | [UM-2] Admin: Manage Seller Company Roles and Permissions | Verified and Pass
386 | [UM-2] Admin: Manage Buyer Company Roles and Permissions | Verified and Pass
525 | Profile Picture not showing correctly on Account Details | Verified and Pass on Dev
537 | Admin – Role should be mandatory field | Verified and Pass on Dev
549 | [UM-2] Newly Added Buyer Company User Edit - Phone Number Required | Verified and Pass on Dev
535 | [UM-2_QA] New User Activation - Resend invite and user clicks on first link , gives message as " Account is already activated " , instead of this show messge as " Activation Link is expired " | Verified and Pass on Dev
435 |  | Verified and Pass
Hot Fix Priority Issues
DE 533 | [production Issue] - All Buyer Addresses are copied to Seller addresses , when ID is same for both buyer and seller | Verified and Pass
DE 522 | Admin Site - Admin able to place orders with seller Draft listings from Admin site | Verified and Pass
DE 501 | Apply Security Patch 9767 | In progress
Sprint 14 - Phase 2
DE 531
DE 524 | [Buyer-Offer] - View offer from PDP is not loading the offer details , for declined offers | Verified and Pass
DE 446
DE 527
DE 526
DE 520
DE 519
DE 518
DE 515
DE 470
DE 459
DE 457
DE 456
DE 442
DE 437
DE 378
DE 309 | Canadian addressses | Pushed back to dev with observations
DE 528
DE 266
New Defects raised
DE 551 |  | Invalid and Closed
DE 525 | [Seller] Profile Picture section is not showing correctly on Account Details | Verified and pass on Staging

## Scenarios
Seller Admin | Add users
Add user and check the positive flow
Add duplicate user and verify the flow
Add duplicate user , when first user has not activated the account
Add same person as buyer and seller and check the roles
Defect 309 | account activation
add new address
edit address
check cargo shipping
same zipcode for buyer and seller
with different trailer types
DE 537 | Request Access | Pass
Back end - admin creating first time users
Front end - admin creatign users
DE 413 | Restricted Limited access User will NOT be able to: - Create and publish listing - Accept/Reject offer - Accept/Reject claims - Edit company info - Invite new company user | Fail | 1. View Listings is failed 2. Accept/Decline buttons are present for offers from Home page

## Observations
No | Date |  |  | Description | Defect ID | Developer Comments
1 |  | Seller - new user Activation Email | Defect - Resend Pending invite and click on first Activation email link | New User Activation - resend invite and user clicks on first link , gives message as " Account is already activated " , instead of this show messge as " Activation Link is expired " | Defect 535 | Defect 535
|  |  | Defect - With Multiple admin user privilages | During new user activation , password set by new user is changing the company admin password also ( when new user is admin and both opened on same browser in different tabs) | Defect 536
|  |  | Suggestion | I suggest there should be only one Admin for one company and Admin privilages should not be available as dropdown option while adding users | Included in Defect 536
|  |  | Suggestion | While creating first admin for a company , Role should be mandatory field | Defect 537
|  |  | Suggestion | Users tab should be available only to Admin users , but not for sellers and buyers | Defect 538
|  |  | Defect - Addresses issue | when seller user role is updated in Admin , seller receives email notification as billing and shipping addresses are updated | Defect 539
|  |  | Suggestion | Invite new sellers - cancel and Send Invitation buttons should be below the form | Defect 540
|  |  | Suggestion | Add users - there should be an upload and download button to easily download and see the sellers list or to upload bulk sellers to a company | Defect 541
|  |  | Suggestion | main company address should not be editable for all sellers, as its main headquarters address(only admin should have privilages to edit main company address) | Defect 542
|  |  | Suggestion | In seller --> Account --> Profile --> There should be a field to show the Role of the seller | Defect 543
|  |  | Suggestion : Admin - Buyer Company | Do not allow to remove buyer company , or show message as there are active buyers associated with this company | Defect 544
| June 21st |  | Suggestion : Admin - Buyer Company | When Buyer company is created there should be a mandatory section to add an Admin for that company instead of again creating the buyer just to add an Admin
| June 21st |  | Staging: Listing Edit | Scenario - - Assign a seller with Restricted Access role - Login as the seller - Click on View Listings - Click on View from any Active listings Notice that its navigating user to Home page . | Updated in Defect 412
| June 21st |  | New user - Roles | One Role is missing and small changs in Add New user role | Updated in Defect 412
| June 21st |  | Suggestion: Edit User --> For Custom Role, show the custom options selected | Display the custom roles selected for that user otherwise even the Admin doesnt know what options are selected under that Custom Role | Defect 545
| June 21st |  | Buyer with Resticted Role Privileges | Buyer with Restricted access - There is no Place order button but able to place an order for this buyer from Admin site | Defect 546
| June 22nd |  | Suggestion Delete pending user requests | There should be an option to delete / edit the pending user requests | Defect 547
| June 23rd |  | Seller - new user with specialized permissions | users are not allowed to edit company info , this should apply to editing of main comapny address also
orders - shipping history dates are different for both buyer and seller
| June 26th |  | Add users - remove user | give some confirmation popup , while removing users as by mistake user can click on remove user and it gets deleted without warning - sorting for columns - checkboxes before each user to select and bulk update
| June 26th |  | Add users - list of users | list should not display all users with pending status , other than Admin privilages
| June 26th |  | Add users - Add new user | able to create custom roles without selecting any options
| June 26th |  | Add users - Add new user | [HTML Tags] Users --> Add new user --> HTML tags are allowed in Add new User input fields Added Defect 553 | Defect 553
| June 26th |  | add users - Custom role - lengthy role name | displays only 50 charcaters on users List for Role , so need to restrict only 50 characters even while entering role name
| June 27th |  | Users tab Suggestion | give the information icon , which shows all information about roles otherwise admin has to click on any eidt or add new user to understand the roles
| June 27th |  | Account - Company Info for restricted Role Suggestion | Company Info tab can be displayed for Restricted Role also , but there should not be an Edit button Company Info is for users information
| June 27th |  | Seller with custom role - no access to messages | Message tab is not present on header section but is present on home page and with view option when clicked on it diverts to home page | Included in US 412
| June 27th |  | Users tab - Edit users | Edited user is going to the end of the users list I guess the users are getting sorted in descending order based on updated date .
| June 27th |  | Users tab Suggestion | Sorting of columns should be present - Display Updated date - Display Updated By column (Show the seller name )
| June 27th |  | Sellers - Orders - offers Suggestion | Introduce Offers status , so that sellers with restricted role can see the status of offers
| June 27th |  | Users Roles - Remove Accept/reject claimscand request a payment info from restricted role | Remove Accept/reject claimscand request a payment info from restricted role User story - 412 | Included in US 412
| June 27th |  | Messages - Show the Seller name - Not just Me | because these messages are displayed for all sellers and they se it as 'Me" , but its some other selelr has replied to it display the seller name instead of ME
| June 27th |  | Custom Role - with Add users | Edit gives error as " This user doesn't exist" | Included in US 412
| June 27th |  | Users tab Suggestion | Why Edit is only to edit the role why not user name and user email address?
|  |  | Users tab - lengthy role names | Role names can be word wrapped for better usability and to avoid scrolling on desktop versions
|  |  | 407 - Observation 1 | Buyer with Restricted Access - Buyer should not have access to Make an offer But is allowed to cancel an offer is this expected ?
|  |  | 407 - Observation 2 | Buyer with restricted Access - Buyer should not have access to checkout But able to proceed to checkout from Offers page
|  |  | suggestion - messages | delete option should not be present for messages or can be given that option to only admin users and offers/messages hould not get displayed company wise , should be for individual users
|  |  | 408 - observation | Buyer with Custom role to Invite new users when clicked on Edit button of existing users displays message as " Unable to Edit the user"
|  |  | Buyer login - product Detail page | on product details page , as user scrolls down "have questions and message seller options are disappeared from page" | Defect 554 Invalid defect its as per design
|  |  | Company Info Update/Addresses Update | when company info or addresses are updated of company , no update notifications are sent to admins what is expected ?
|  |  | RFQ - Create new RFQ | Create New RFQ - Describe Shipping tab - End date Next month dates should not be grayed out ( its just greyed out and user able to select the dates for next month)
|  |  | Buyer - Offers - Cancelled Offer | As Buyer , cancel the Offer Navigate to My Activity --> Offers --> View button for cancelled Offer View button shows as disabled , but is actually cliackable and user can view the cancelled offer details Expected - View button should display as enabled and clickable
|  | Defect 309 | Buyer - checkout page - add new address | Country is showing only USA , not canada
Seller - New seller activation process - there is no Country dropdown
|  |  | Seller - Account settings - Addresses - Edit existing address | State is not displaying and country is showing as USA for cananda address
|  |  | Seller - Account settings - Addresses - Add new address | select should not be an option in dropdown no blank space in dropdown values state can be disabled till country is selected instead of showing messgae as select country first
|  |  | Add new address on checkout page | zip code validation displayed for canada address both shipping and billing addresses (that validation is applicable only for USA zipcodes)
|  |  | From Admin Poratl - Seller Addresses | Edit existing canada address , even though country is cananda , USA states are displayed in State dropdown (Should be canada States)
delete a destination address when order is in shipping mode
caller type in request and response
mileage per mile is different for same zipcode
|  | Suggestion | when seller company is created in Admin then go to sellers - there should be an option to create a new seller form there itself just a button , which again diverts the user to add new seller page only
|  |  | Admin - Create seller - Phone number mandatory asterisk is missing | Defect 551
|  |  | [Dev Environment] Seller Listings - Internal ID is not displaying properly on Listings page | Defect 552
|  |  | Shipping history dates are showing different for buyer and seller | Sent mail with screen shots to Geoff

## Clarifications
Item No | Clarifiction
395 | I can create a new Company User by providing an approved company email address Clarification - How do we validate approved company email address? Can admin of company abc.com can send invites to only abc.com domain users?
1. Create seller company 2. Create a seller under this company with no role assigned 3. Activate the seller company how many emails does Seller email address receive?